## Gantt Chart
MSc Cybersecurity · Sheffield Hallam University · 55-710260 · Dr Sina Pournouri
Dissertation Project Gantt Chart — Integrity Assurance in Planetary Defense: NEO Tracking Pipeline Cybersecurity
Project started: March 2026 ¦ RMS deadline: 18 June 2026 ¦ Dissertation: September 2026 ¦ Working time: ~6 months
Task / Activity |  | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026
◆ Project Start — NEO Cybersecurity | March 2026 |  |  | ◆ | March 2026
PHASE 1 — Literature & RMS Proposal (Mar – Jun 2026)
Topic re-evaluation & scoping | Define research question & objectives |  |  | Topic re-evaluation & scoping
Literature survey | SIN, SDLS, ADES, CCSDS, space cyber |  |  | Literature survey
RMS proposal write-up | 2,500-word research proposal |  |  |  | RMS proposal write-up
Supervisor meetings | Ongoing throughout project |  |  | Supervisor meetings
◆ RMS SUBMISSION DEADLINE | 18 June 2026 | [5 empty] | ◆ | 18 June 2026
PHASE 2 — Data Collection & Simulation (Jun – Aug 2026)
MPC API data collection | Apophis & Bennu tracklet retrieval | [5 empty] | MPC API data collection
ADES format synthesis | XML/JSON pipeline construction | [5 empty] | ADES format synthesis
GMAT & Python environment | Tool setup & dependencies | [5 empty] | GMAT & Python environment
Adversarial injection module | RA/Dec perturbation — 3 archetypes | [5 empty] | Adversarial injection module
Orbital propagation runs (GMAT) | 50+ simulation scenarios | [6 empty] | Orbital propagation runs (GMAT)
MCDA risk scoring framework | L, V, A, I, C criteria | [6 empty] | MCDA risk scoring framework
◆ Interim supervisor review | August 2026 | [7 empty] | ◆ | August 2026
PHASE 3 — Writing & Submission (Jul – Sep 2026)
Draft all dissertation chapters | Intro, lit review, methodology | [6 empty] | Draft all dissertation chapters
Results & discussion write-up | Analysis, findings, implications | [7 empty] | Results & discussion write-up
Supervisor full draft review | Feedback integration | [7 empty] | Supervisor full draft review
Final revisions & proofread | Formatting, references, submission | [7 empty] | Final revisions & proofread
◆ DISSERTATION SUBMISSION | September 2026 | [8 empty] | ◆
LEGEND
■ Planning / RMS | ■ Literature | ■ Data collection | ■ Simulation | ■ Writing | ■ Supervision | ■ Milestone | ■ Deadline